## Estimated Efforts
Activities | Steps / Actions | Estimated Time (Hours) | Comments | Internal referencse |  |  | Complexity parameters
Requirement Understanding and setup | [6 empty] | Number of UI Element
Understanding the manual flow of the process | Manual walk through of application | 5 |  |  |  |  | Selector options available
Documentation | Basic documentation of process understanding and PDD and SDD | 21 |  |  |  |  | Web responsiveness
Environment setup | Required hardware, software & code repo setup | 2 |  |  |  |  | Data preprocessing involved
| Installation of all required application | 1 |  |  |  |  | Number of field validation
Total Efforts for requirement and setup |  | 29 |  |  |  |  | Number of Pop-Ups
Tramada build basics - Add Debtor | [6 empty] | Start Date |  | 2023-05-15 | 2023-05-23 | 2023-06-13 | TBD
Debtor Flags - General Flags | Set up | 15 | [5 empty] | Resources | Initial setup | Development | Deployment | Monitoring
Debtor Flags - General Flags | Payment Gateway - PG | 3 |  |  |  |  | Architect |  | 1 | 0.25 | 0.25 | 0
Debtor Flags - General Flags | Charge Back | 0.5 |  |  |  |  | RPA Engineer |  | 1 | 1 | 1 | 1
Debtor Flags - General Flags | Client Profile | 0.75 |  |  |  |  | Man Days |  | 5 | 38 | 10 | 5 | depend on time for 4000 records processing + 15%
Debtor Flags - General Flags | Client Profile- Set mandatory fields | 0.5 |  |  |  |  | Working days |  | 5 | 38 | 10 | 5
Debtor Flags - General Flags | Department Levels | 0.75
Debtor Flags - General Flags | Client Email Address Validation | 0.5
Debtor Flags - General Flags | Booking Upload | 5.75 | [5 empty] | Rate | Initial setup | Development | Deployment | Monitoring | Total
Debtor Flags - General Flags | SSO for New Clients | 0.5 |  |  |  |  | Duration (weeks) |  | 1 | 3 | 1 | TBD
Debtor Flags - General Flags | Airhelp | 1 |  |  |  |  | Architect | 1000 | 1 | 1 | 0.25 | 0.5 | 4062.5
Debtor Flags - General Flags | Manual Booking Documents from Email Address Default | 1 |  |  |  |  | RPA Engineer | 1000 | 1 | 1 | 1 | 1 | 4250
Debtor Flags -Booking Defaults | Defaults | 6.25 | [10 empty] | 8312.5
Debtor Flags -Debtor Invoice Defaults | Defaults | 13.75 | [5 empty] | Mins (Manually) |  |  | Mins (RPA) | Total hrs (RPA)
Debtor Flags -Debtor Invoice Defaults | Auto Invoice Email Resolve Order | 5.25 |  |  |  |  | Total transactions |  |  | 4000
Debtor Flags -Debtor Invoice Defaults | Auto Invoice Email CC | 4.25 |  |  |  |  | Time per transaction (with inbuilt automation) | 45 | mins | 2857 | 0 | 0 |  | 5
Debtor Flags - Corporate Savings Defaults | Defaults | 9.5 |  |  |  |  | Time per transaction (manually) | 95 | mins | 1143 | 0 | 0 |  | 2
Debtor Flags - Auto Invoice Configuration | Booking Selection Criteria | 1.25 |  |  |  |  | % of transactions with inbuilt automation | 71.43% | [5 empty] | 420 | 415
Debtor Flags - Auto Invoice Configuration | Ticket Segment Checks | 0.5 |  |  |  |  | Transactions per person per day | 7
Debtor Flags - Auto Invoice Configuration | Ticket Type | 3 |  |  |  |  | Manual resources team size | 5
Debtor Flags - Auto Invoice Configuration | Email Notification | 0.5 |  |  |  |  | Duration of processing manually | 114.2857 | days |  |  | 0
Debtor Flags - Auto Invoice Configuration | Error Notification | 0.25 |  |  |  |  | Duration of processing manually | 5.7143 | months |  |  | 0
Debtor Flags - Auto Invoice Configuration | Invoice Format | 0.6 | [9 empty] | 0%
Online/Offline Set up -Defaults | Set up | 5.5
Online/Offline Set up - Document Email Configs | Add Email configuration | 1
Debtor Interfaces - Company Access | Access | 0.25 |  |  |  |  | Considerations:
Debtor Interfaces - Company Access | CPI Setup | 0.75 |  |  |  |  | - Need of rerun for any failed scenarios |  |  | Manual | RPA
[9 empty] | OneTime cost | 0 | 8312.5
Code Review | Review the code | 21 |  |  |  |  | Add manual steps for the additional work done manually (+55 mins) |  | Resources (#) | 5 | 1
Code fix after review | Fix the changes | 14 |  |  |  |  | Based on number of UiPath licenses - efforts/timelines may vary |  | Resource ($) | 850 | 1000
Testing | Testing code with few samples | 28 |  |  |  |  | Salesforce and any other applications of our interest are up 24x7 |  | Duration | 6 | 0
Bug fix after testing | Bug fixes if requried | 14 |  |  | 21 | <- hrs (Bot run time per day) |  |  | Cost | 25500 | 8312.5
SERKO | [8 empty] | Saving | 67.4%
Login-Serko | Login to Serko App | 0.25 | [6 empty] | Dev Duration | 0 | 3
Admin |  | 0.75 | [6 empty] | RoI in time saved | 3 | months
Corporate site | Corporate Structure
Corporate site | Search --> CT_Connection -Master Profile*** | 0.25
Corporate site | Navigate to Master | 0.25
Corporate site | Click 'Clone' | 0.25
Corporate site | Goes to Corporate clone page
Corporate site | Enter code and Name, check 'do you want to be master corporate' | 0.75
Corporate site | Save and Reload | 0.25
Corporate site | Changes to be done on cloned page has not shown | 5
Corporate site | Redirect to Home page -> go to Hotel Policy | 1
Corporate site | Go to Car Policy | 1
Corporate site | Go to Air Policy | 1
Admin -> Global settings | Role Group -> Search Master | 0.25
Admin -> Global settings | Clone -> Master Authorizer, Master travel booker, Master Traveller -Mandatory | 1.75
Admin -> Traveller profile | Create new profile
Admin -> Traveller profile | Personal info | 6.5
Admin -> Traveller profile | Role Groups | 1.5
Admin -> Traveller profile | Profile custom fields | 3
Admin -> Traveller profile | After save, page lands on Profile administration page
Admin -> Traveller profile | Repeat steps for Authoriser and semi authoriser [Traveler booker ?] | 21
Admin -> Template builder | Templates | 3
Admin -> Corporate structure | Search created profile | 0.25
Admin -> Corporate structure | Update fields which has 'Team Queue' and 'Ops email address text' associated with profile | 1.25
Integration of Code
Total of process development |  | 208.1
Deployment | Deploy on production | 24
Testing on Prod | Test on production | 28
Total of deployment |  | 52
Buffer (% of total efforts) | 25% | 65.025
| Total - Implementation time | 325.125
| Working hrs per day | 7
| Team Size | 1
| Requirement understanding & Set up | 29
| Number of days | 47
Considerations: | Access to Staging or Sandbox environment
Sample Input file is ready before development
Actual details of the data entry will be shared before the actual work. Based on the same, timelines may vary
General Queries | 1. Do we have any acknowledgement on saving/submission of each page/form
2. Debtor Add - Overview Section - Purpose of Edit button
3. Debtor Employee Types - Add Type - Is it pop-up or adding entry in table directly?
4. In Global setting, after cloning - Master Authorizer, Master travel booker, will it go to traveller profile page for amendment to do as per required data
5. In Hotel policy section : How to configure this policy, either just by cloning and adding it OR Configuring manually, if need to configure manually, what is the procedure
6. In Car policy section : How to configure this policy, either just by cloning and adding it OR Configuring manually, if need to configure manually, what is the procedure
7. In Air policy section :How to configure this policy, either just by cloning and adding it OR Configuring manually, if need to configure manually, what is the procedure
8. What needs to be done in create PNR template?
9. How to link Air policy with car and hotel policy? Will it get automatically linked?

## RoI - UiPath
Number of days in a month | 20 | Resources | Rate | Design |  | Development |  | Total Cost
Customer onboarding resource Rate | 3000 |  |  | Allocation | Months | Allocation | Months | 6562.5
Before Automation: |  | RPA Architect | 1000 | 1 | 0.25 | 0.25 | 2.4 | 850
Team size | 2 | RPA Developer | 1000 | 1 | 0.25 | 1 | 2.4 | 2650 | 2 more months for support/maintenance/enhancements
Average time per customer (mins) | 480 | RPA Developer | 1000 | 0 | 0 | 1 | 2.4 | 2400 | 4 more months part time for support/maintenance
Customer onboarded per day | 1 | Project Manager | 1000 | 0.25 | 0.25 | 0.25 | 2.4 | 662.5 | post support period, rates on hourly basis or extension as needed
After Automation:
Team size | 1 |  | Annual licensing |  |  | Monthly licensing |  |  | Monthly uploading |  |  | Annual licensing |  | Monthly uploading
Average time per Customer (mins) | 60 |  | Breakeven: | 10 months |  | Breakeven: | 10 months |  | 1000+ additional properties being uploaded by break even. |  | Month | Cost - Before | Cost - After | Properties Before | Properties After
Customer onboarded per day | 8 |  | 60000 | 55402.5 |  | 60000 | 52262.5 |  |  |  | 1 | 6000 | 28402.5 | 20 | 140
Implementation: |  | Development | 0 | 6562.5 | 1 | 0 | 6562.5 | 1 |  |  | 2 | 12000 | 31402.5 | 40 | 280
% automation considered | #REF! | License cost | 0 | 18840 | 1 | 0 | 0 | 1 |  |  | 3 | 18000 | 34402.5 | 60 | 420
Development cost (one time) | 6562.5 |  | Before | After |  | Before | After |  | Before | After | 4 | 24000 | 37402.5 | 80 | 560
UiPath Unattended bot license (monthly) | 1570 | Month 1 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 20 | 160 | 5 | 30000 | 40402.5 | 100 | 700
UiPath Unattended bot license (annual) | 18840 | Month 2 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 40 | 320 | 6 | 36000 | 43402.5 | 120 | 840
Server (MS Windows Server 2019 with std config): 01 |  | Month 3 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 60 | 480 | 7 | 42000 | 46402.5 | 140 | 980
Database - use existing |  | Month 4 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 80 | 640 | 8 | 48000 | 49402.5 | 160 | 1120
Bot run time (mins) for 1 Customer (Avg setup) | 15 | Month 5 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 100 | 800 | 9 | 54000 | 52402.5 | 180 | 1260
Total Customer profile a bot can automate in 24 hrs | 96 | Month 6 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 120 | 960 | 10 | 60000 | 55402.5 | 200 | 1400
Max manual resources we can have per bot | 6.8571 | Month 7 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 140 | 1120 | 11 | 66000 | 58402.5 | 220 | 1540
Considerations |  | Month 8 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 160 | 1280 | 12 | 72000 | 61402.5 | 240 | 1680
UiPath cost may vary |  | Month 9 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 180 | 1440
% automation coverage may vary |  | Month 10 | 6000 | 3000 | 1 | 6000 | 4570 | 1 | 200 | 1600
Development efforts/cost may vary |  | Month 11 | 6000 | 3000 | 0 | 6000 | 4570 | 0 | 220 | 1760
Implemented bot can automate more customer profiles a day |  | Month 12 | 6000 | 3000 | 0 | 6000 | 4570 | 0 | 240 | 1920
This can be hosted over cloud and cost to be calculated
existing manager to look after this later
Developer for maintenance full time > part time > hourly
Other benefits
Better accuracy in Customer onbaording
RoI will be faster for a bigger team size
Resources can be repurposed based on skills
post break even monthly 60% + savings
automation can improve up to 75-80%
Below are Prerequisites for Installation of orchestrator. Install these on Orchestrator instance.
1. PowerShell - minimum required version: 4.0.
2. .NET Framework - minimum required version: 4.7.2.
3. IIS - minimum required version: 8. This is part of the Web Server (IIS) role. Following roles needs to be installed.
1. Expand Web Server (IIS) > Web Server > Common HTTP Features. The list contains the following items:
1. Default Document
2. HTTP Errors
3. Static Content
2. Expand Web Server (IIS) > Web Server > Security. The list contains the following items:
1. Request Filtering
2. URL Authorization
3. Windows Authentication
3. Expand Web Server (IIS) > Web Server > Application Development. The list contains the following items:
1. ASP.NET45
2. .NET Extensibility 4.5
3. Application Initialization
4. ISAPI Extensions
5. ISAPI Filter
6. WebSocket’s
4. Expand Web Server (IIS) > Web Server > Management Tools. The list displays the following items: IIS Management Console
5. Access Add Roles and Features Wizard > Features to enable the following item: Client for NFS.
4. ASP.Net Core IIS Module: Version should be part of the Hosting Bundle. Can be found here https://dotnet.microsoft.com/download/dotnet/thank-you/runtime-aspnetcore-3.1.5-windows-hosting-bundle-installer
5. URL Rewrite Module: Can be found here https://www.iis.net/downloads/microsoft/url-rewrite
6. SSL Certificate
1. Open IIS manager – Server certificate
2. Click on Self-signed certificate.
3. Specify name of the certificate, keep certificate store as Personal.
4. Click ok. (Keep the name of certificate for further use.)