## Amagi Portal(Example 3)
Activities | Steps / Actions | Radio button (#) | Drop down (#) | Check box (#) | Button (#) | Text fields (#) | Calendar (#) | Pop-up (#) | Messages (#) | Additional %age | Total Time (MINS) | Comments/Assumptions | Internal references | Exceptions considered. | Fields/Actions | Mins | Additional /Complex
Pilot Requirement Understanding and setup | [14 empty] | Radio | 30 | 10%
Understanding the manual flow of the process | Manual walk through of application | [9 empty] | 360 |  |  |  | Drop Down | 40 | 50%
Documentation | Basic documentation of process understanding and consideration for POC | [9 empty] | 600 |  |  |  | Checkbox | 35 | 22.5
Environment setup | Required hardware, software & code repo setup | [9 empty] | 420 |  |  |  | Button | 30 | 20
| Dev environment setup | [9 empty] | 420 |  |  |  | Text field | 30 | 3000%
Process Development | [14 empty] | Calendar | 60 | 40%
build basics | [14 empty] | Pop-up | 50
Read config file (Assuming config file present inside config folder inside shared location and bot has access to it ). | Read the config file and Extract data like credentials, file paths, mailIDs etc from the file. | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 20% | 72 | considering file read by dictionary variable |  | 1 file not readable bcz currepted data | Messages | 15
Go to Amagi portal address and click on sign in after entering respective details. | 1. Navigate to the Amagi portal enter the ID and password. 2.Click on signin button. 3.Verify the screen with expected result. |  |  |  | 1 | 2 |  | 1 | 1 | 10% | 170.5 | 1.Considering simple login portal it contain username, password field and login button. 2.After error considering we need just update the variable like Start and End time, client, filename.3.Assuming after login it will show popup and message to verify successful login. | text fields, button,popup, message | 1.invalid/expired/empty username or password
Bot click on download report tab | clicking on downlod report tab |  |  |  | 1 |  |  |  |  | 20% | 36 | Here we are clicking on download report tab | button
Under Time parameter 1.bot will click on interval dropdown button-select monthly 2.bot will click on data range dropdown -select last month 3. Bot will click on Timezone dropdown-selct 'US/Eastern' | 1.Click on Time parameter tab -click on interval dropdown button-select monthly. 2.Click on Time parameter tab -click on data range dropdown-selet last month 3..Click on Time parameter tab -click on Timezone dropdown button-select 'US/Eastern' |  | 3 |  | 3 |  |  |  |  | 10% | 231 | Considering 1 button for selecting tab and click on dropdown button and then selecting option | button , dropdown
under content parameter bot will click on' all ' radio button | 1.click on content parameter 2. select 'all' radio buttons | 1 |  |  | 1 |  |  |  |  | 10% | 66 | Considering that we have to click on content parameter first and then select radio button named as 'All' | radio button , Button
Bot click on generate report button | 1.clicking on generate report button . 2.giving delay time 3.bot confirms report is generated |  |  |  | 1 |  |  | 1 | 1 | 10% | 104.5 | Considering that after generating report it will give popup and message so that we can verify report is generated. | button , popup , message | .
Bot clicks on download button/icon below Actions section to download the report | 1.Click on 'Action section' 2.bot will click on download report button under action section |  |  |  | 2 |  |  |  |  | 10% | 66
Bot collects CSV file.Bot rename the file as per convention | Use of rename activity |  |  |  |  | 1 |  |  |  | 10% | 33
Bot connects to VPN for Whip Customer AWS instance | considering check point VPN . Enter username and password. Then click on login. Wait few sec for auth otp. Enter generated OTP and click connect |  |  |  | 2 | 3 |  |  |  | 20% | 180 | considering like the check point VPN . Enter username and password. Then click on login. Wait few sec for auth otp. Enter generated OTP and click connect |  | 1.invalid/expired/empty username or password 2.If expected portal wasn't received after logging in. 3. Auth OTP is invalid/wrong
Bot logs into S3 bucket | Assuming bot will login to s3 portal by entering username and password and login button |  |  |  | 1 | 2 |  |  |  | 10% | 99 | 1.considering its login portal it contain email password field and login button. 2.Aftter getting error assum that we need just update the variable like Start and End time, client, filename,error point. | text fields, button | 1.invalid/expired/empty username or password 2.If expected portal wasn't received after logging in.
Bot drops the renamed .CSV into destination folder | Move .csv file from source folder to the destination folder |  |  |  |  | 2 |  |  |  | 10% | 66 | Assuming there is one shared location for source and destination and bot has its access. |  | 1.source and destination folder not accessible to bot
Bot loads page for ingester | Redirect to the respective ingestor website |  |  |  |  | 1 |  |  |  | 10% | 33
Bot clicks the IngestNow button | click on button |  |  |  | 1 |  |  |  |  | 0 | 30 | Assuming it is a simple button
Bot checks original destination folder on Customer S3 folder to verify the file has been removed | Bot will check the status of file |  |  |  |  | 2 |  |  |  | 10% | 66 | Checking of the respective folder for absence of file will contain logical part.
File ingested into Customer CVM server or placed in error folder | Select the file . Pop up will appear to select the file location and upload.(Assumption) |  |  |  | 2 |  |  | 1 |  | 20% | 132
Bot dashboard is updated with timestamp (start and end), client, filename, success | Bot will generate the logs for the respective fields(Assumption) |  |  |  |  | 3 |  |  |  | 10% | 99 | Considering dashbord as for showing logs .
For exception handling | [9 empty] | 20% | 120
Unit testing, reviews, fixes | [9 empty] | 20% | 320.8
Bug fix after testing | Bug fixes if required | [8 empty] | 15% | 240.6
Integration of Code | [10 empty] | 300
Total of process development | [10 empty] | 42 | In Hrs
Deployment | Orchestrator set up : A. IIS configuration : 1. Web server - HTTP features 2. Web server - security 3. Web server - Application development 4. Web server - Web sockets 5. Web server - Management tools - Roles and features enable B. SSL server configuration | [9 empty] | 14
Deployment | Bot deployment | [9 empty] | 7
Deployment | Studio configuration | [9 empty] | 7
Testing on Prod | Test on production | [9 empty] | 14
Total of deployment | [10 empty] | 42 | In Hrs
Buffer (% of total efforts) | 10% | [9 empty] | 9
| Total - Implementation time | 5580 | 93
| Working hrs. per day | 7
| Team Size | 1
| Requirement understanding & Set up | 1800 | 30
| Number of days | 18
Considerations: | Access to Staging or Sandbox environment
Sample Input file is ready before development
Actual details of the data entry will be shared before the actual work. Based on the same, timelines may vary
Considering credentials and access of portal are handy with the developers.