## example2-Pluto- partner-portal
Activities | Steps / Actions | Radio button (#) | Drop down (#) | Check box (#) | Button (#) | Text fields (#) | Calendar (#) | Pop-up (#) | Messages (#) | Additional %age | Total Time (MINS) | Comments/Assumptions | Internal references | Exceptions considered. | Fields/Actions | Mins | Additional /Complex
Pilot Requirement Understanding and setup | [14 empty] | Radio | 30 | 10%
Understanding the manual flow of the process | Manual walk through of application | [9 empty] | 360 |  |  |  | Drop Down | 40 | 50%
Documentation | Basic documentation of process understanding and consideration for POC | [9 empty] | 600 |  |  |  | Checkbox | 35 | 22.5
Environment setup | Required hardware, software & code repo setup | [9 empty] | 420 |  |  |  | Button | 30 | 20
| Dev environment setup | [9 empty] | 420 |  |  |  | Text field | 30 | 30
Process Development | [14 empty] | Calendar | 60 | 40%
build basics | [14 empty] | Pop-up | 50
RPA Bot starts process on configurable schedule with a specific file target | Read the config file and Extract data like credentials, file paths, mailIDs etc from the file. | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 20% | 72 | considering file read by dictionary variable |  |  | Messages | 15
RPA Bot goes to Pluto portal address.Go to pluto portal address and click on sign in after entering respective details.i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | 1. Navigate to the pluto portal enter the ID and password. 2.Click on signin button. 3.Verify the screen with expected result. |  |  |  | 1 | 3 |  |  |  | 15% | 138 | Assuming pluto portal address has simple URL. |  | If URL is not present it will handle exception
Bot clicks on 'PlutoTV External' folder i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | bot will click on the 'Pluto External' folder. |  |  |  | 1 |  |  | 1 | 1 | 5% | 99.75 |  |  | if folder is not present it will show popup and message with details and handle exception
Bot clicks on 'Content Partner' folder i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | Bot will click on the 'Content Partner' folder. |  |  |  | 1 |  |  | 1 | 1 | 10% | 104.5 |  |  | if folder is not present it will show popup and message with details and handle exception
Bot clicks on 'Partner Dashboard' folder i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | bot will click on the 'Partner Dashboard' folder. |  |  |  | 1 |  |  | 1 | 1 | 10% | 104.5 |  |  | if folder is not present it will show popup and message with details and handle exception
Bot clicks on 'MONTHLY PARTNER DASHBOARD' folder i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | bot will click on the 'Monthly partner' folder. |  |  |  | 1 |  |  | 1 | 1 | 15% | 109.25 |  |  | if folder is not present it will show popup and message with details and handle exception
Bot selects expected values on dropdown filters 'DATE', 'PARTNER', 'BRAND', 'CHANNEL', 'SERIES' and 'COUNTRY' i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | bot will select the values from the dropdowns named like 'DATE', 'PARTNER', 'BRAND', 'CHANNEL', 'SERIES' and 'COUNTRY'. |  | 6 |  | 6 |  | 1 | 1 | 1 | 15% | 626.75 | Assuming there is one dropdown which has 6 options to select. |  | if folder is not present it will show popup and message with details and handle exception
Bot clicks/hovers on 'Choose a format to download' button on the top right - which opens all format options under this button a. Bot clicks on 'Crosstab' b. New window pops 'Download Crosstab' - bot checks (checkbox) 'Monthly Series Crosstable' c. Bot clicks on 'Download' button i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | bot will click on "Choose a format to download" button which will open all format after that bot will click 'Crosstab' which will open new window of 'Download Crosstab' and will check for ''Monthly Series Crosstable'' and then bot will click on 'Download button'. |  |  | 1 | 3 |  |  | 1 | 1 | 10% | 209 | Assuming the 'Monthly Series Crosstable' is a checkbox. |  | If Bot fails at this stage it posts to dashboard the it will 'Handling the exception which is showing Pop-up and message with required details (Start and End time, client, filename, error point)
Bot renames files as per naming convention | Use of rename activity |  |  |  | 1 | 1 |  |  |  | 10% | 66
Bot connects to VPN for Whip Customer AWS instance | considering check point VPN . Enter username and password. Then click on login. Wait few sec for auth otp. Enter generated OTP and click connect |  |  |  | 2 | 3 |  |  |  | 0 | 150
Bot logs into S3 bucket | Assuming bot will login to s3 portal by entering username and password and login button |  |  |  | 1 | 2 |  |  |  | 10% | 99
Bot drops the renamed file into destination folder | downloaded renamed file will be placed in destination folder inside S3 Bucket. |  |  |  |  | 2 |  |  |  | 5% | 63
Bot loads page for ingester | Redirect to the respective ingestor website |  |  |  | 1 | 1 |  |  |  | 5% |  | Considering ingester has its own URL.
Bot clicks the IngestNow button | Clicking on the IngetNow button. |  |  |  | 1 | [6 empty] | Assuming it is a simple button
Bot checks original destination folder on Customer S3 folder to verify the file has been removed | Bot will check the status of file |  |  |  | 2 |  |  |  |  | 15% |  | Checking of the respective folder for absence of file will contain logical part.
File ingested into Customer CVM server or placed in error folder | Select the file . Pop up will appear to select the file location and upload.(Assumption) |  |  | 2 | [5 empty] | 20% |  | Checking of the respective folder for presence of file will contain logical part. |  | if destination folder is missing it will handle the exception
Bot dashboard is updated with timestamp (start and end), client, filename, success or failure | Bot will generate the logs for the respective fields(Assumption) |  |  |  | 3 |  |  | 1 | 1 | 20%
For exception handling | [10 empty] | 120
Unit testing, reviews, fixes | [9 empty] | 20% | 392.35
Bug fix after testing | Bug fixes if required | [8 empty] | 15% | 294.2625
Integration of Code | [10 empty] | 300
Total of process development | [10 empty] | 50 | In Hrs
Deployment | Orchestrator set up : A. IIS configuration : 1. Web server - HTTP features 2. Web server - security 3. Web server - Application development 4. Web server - Web sockets 5. Web server - Management tools - Roles and features enable B. SSL server configuration | [9 empty] | 14
Deployment | Bot deployment | [9 empty] | 7
Deployment | Studio configuration | [9 empty] | 7
Testing on Prod | Test on production | [9 empty] | 14
Total of deployment | [10 empty] | 42 | In Hrs
Buffer (% of total efforts) | 10% | [9 empty] | 10 | in hrs
| Total - Implementation time | 6120 | 102
| Working hrs. per day | 7
| Team Size | 1
| Requirement understanding & Set up | 1800 | 30
| Number of days | 19
Considerations: | Access to Staging or Sandbox environment
Sample Input file is ready before development
Actual details of the data entry will be shared before the actual work. Based on the same, timelines may vary
Considering credentials and access of portal are handy with the developers.