## Exmaple1-Wurl
Activities | Steps / Actions | Radio button (#) | Drop down (#) | Check box (#) | Button (#) | Text fields (#) | Calendar (#) | Pop-up (#) | Messages (#) | Additional %age | Total Time (MINS) | Comments/Assumptions | Internal references | Exceptions considered. | Fields/Actions | Mins | Additional /Complex
Pilot Requirement Understanding and setup | [14 empty] | Radio | 30 | 10%
Understanding the manual flow of the process | Manual walk through of application | [9 empty] | 360 |  |  |  | Drop Down | 40 | 50%
Documentation | Basic documentation of process understanding and consideration for POC | [9 empty] | 600 |  |  |  | Checkbox | 35 | 22.5
Environment setup | Required hardware, software & code repo setup | [9 empty] | 420 |  |  |  | Button | 30 | 20
| Dev environment setup | [9 empty] | 420 |  |  |  | Text field | 30 | 30
Process Development | [14 empty] | Calendar | 60 | 40%
build basics | [14 empty] | Pop-up | 50
RPA Bot starts process on configurable schedule with a specific file target | Read the config file and Extract data like credentials, file paths, mailIDs etc from the file. | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 20% | 72 | considering file read by dictionary variable |  | if file path not accessible it will handle exception | Messages | 15
RPA Bot goes to Wurl portal address.Go to wurl portal address and click on sign in after entering respective details.i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | 1. Navigate to the Wurl portal enter the ID and password. 2.Click on signin button. 3.Verify the screen with expected result. |  |  |  | 2 | 2 |  | 1 | 1 | 10% | 203.5 | Assuming login portal contain 2 text fileds 1 button | text fields, button | it will handle exception if url is not found ,credentials doesn’t match and if login button is not clickable
Bot selects the most recent portal version that is not in progress i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | bot will select the most recent portal version |  | 1 |  |  |  |  | 1 | 1 | 20% | 126 | Considering for selecting the recent version will need 1 dropdown | Drop down | If bot fails to find recent version as dropdown element it will handle exception so we need 1 popup and message .
Bot selects 'Aggregate Data' tab i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | bot will select 'Aggregate Data' tab |  |  |  | 1 |  |  | 1 | 1 | 10% | 104.5 |  | button | it will hanle exception if tab option is disabled.
Bot selects filter options (data range, data grain, episode/series) if needed i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | bot will click on the filters option if there is need. |  |  | 4 |  |  |  | 1 | 1 | 15% | 235.75 | Considering 4(data range, data grain, episode/series) filters by clicking on checkboxex | checkboxs | it will hanle exception if tab option is disabled.
Bot right click inside the report and hovers cursor over the 'Export' and bot clicks on .CSV to download data i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | 1. bot wil right click inside report 2.bot will hovers cursor over the 'Export' 3. bot will clicks on .csv to download data. |  |  |  | 3 |  |  | 1 | 1 | 15% | 178.25 | Considering the clicking is done in report page and Hover over the export. Click to select .csv format and download. | buttons | 1. It will handle the exceptio if not able to do right click inside report 2.It will handle exception if file is not getting selection and not able to dowload.
Bot selects 'Asset Data' tab i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point, but continue to the next file | bot will click on the asset data tab |  |  |  | 1 |  |  | 1 | 1 | 10% | 104.5 | consider simple click on 'assert data 'tab | button | it will hanle exception if tab option is disabled.
Bot drops the renamed file into destination folder | Use of rename activity |  |  |  |  | 1 |  | 1 | 1 | 10% | 104.5 |  |  | 1. if .csv element is not found it will Handling the exception 2. if the rename text field in not found it will Handling the exception
Bot connects to VPN for Whip Customer AWS instance | considering check point VPN . Enter username and password. Then click on login. Wait few sec for auth otp. Enter generated OTP and click connect |  |  |  | 2 | 3 |  |  |  | 20% | 180 | considering like the check point VPN . Enter username and password. Then click on login. Wait few sec for auth otp. Enter generated OTP and click connect | button , text filed | 1.if username/password is invalid it will Hanlding exception 2.if AWS istance unable to open it will Handling the exception . 3. if Auth OTP is invalid/wrong it will Handling the exception
Bot logs into S3 bucket | Assuming bot will login to s3 portal by entering username and password and login button |  |  |  | 1 | 2 |  |  |  | 20% | 108 | 1.considering s3 is login portal it contain email password field and login button. 2.Aftter getting error assum that we need just update the variable like Start and End time, client, filename,error point. | text fields, button | 1.invalid/expired/empty username or password 2.If expected portal wasn't received after logging in.
Bot drops the renamed .CSV into destination folder | Move .csv file from source folder to the destination folder |  |  |  |  | 2 |  |  |  | 10% | 66 | Assuming there is one shared location for source and destination and bot has its access. |  | 1.source and destination folder not accessible to bot
Bot loads page for ingester | Redirect to the respective ingestor website |  |  |  |  | 1 |  |  |  | 10% | 33 |  |  | Handling the exception if respective URL is not get open.
Bot clicks the IngestNow button | click on button |  |  |  | 1 |  |  |  |  | 0 | 30 | Assuming it is a simple button | button | bot unable to find the IngestNow Button.
Bot checks original destination folder on Customer S3 folder to verify the file has been removed | Bot will check the status of file in source folder |  |  |  |  | 2 |  |  |  | 15% | 69 | Checking of the respective folder for absence of file will contain logical part. |  | Handling the exception for the file is present In source folder
File ingested into Customer CVM server or placed in error folder | Select the file . Pop up will appear to select the file location and upload.(Assumption) |  |  |  | 2 |  |  |  |  | 20% | 72 | Checking of the respective folder for presence of file will contain logical part. |  | Handling the exception for the file is absent in destination folder
Bot dashboard is updated with timestamp (start and end), client, filename, success | Bot will generate the logs for the respective fields(Assumption) |  |  |  |  | 3 |  |  |  | 15% | 103.5 | Considering dashbord as for showing logs .
For exception handling | [10 empty] | 120
Unit testing, reviews, fixes | [9 empty] | 25% | 477.625
Bug fix after testing | Bug fixes if required | [8 empty] | 20% | 382.1
Integration of Code | [10 empty] | 300
Total of process development | [10 empty] | 52 | In Hrs
Deployment | Orchestrator set up : A. IIS configuration : 1. Web server - HTTP features 2. Web server - security 3. Web server - Application development 4. Web server - Web sockets 5. Web server - Management tools - Roles and features enable B. SSL server configuration | [9 empty] | 14
Deployment | Bot deployment | [9 empty] | 7
Deployment | Studio configuration | [9 empty] | 7
Testing on Prod | Test on production | [9 empty] | 14
Total of deployment | [10 empty] | 42 | In Hrs
Buffer (% of total efforts) | 10% | [9 empty] | 10 | in hrs
| Total - Implementation time | 6240 | 104
| Working hrs. per day | 7
| Team Size | 1
| Requirement understanding & Set up | 1800 | 30
| Number of days | 20
Considerations: | Access to Staging or Sandbox environment
Sample Input file is ready before development
Actual details of the data entry will be shared before the actual work. Based on the same, timelines may vary
Considering credentials and access of portal are handy with the developers.