## Example 4-Google
Activities | Steps / Actions | Radio button (#) | Drop down (#) | Check box (#) | Button (#) | Text fields (#) | Calendar (#) | Pop-up (#) | Messages (#) | Additional %age | Total Time (MINS) | Comments/Assumptions | Internal references | Exceptions considered. | Fields/Actions | Mins | Additional /Complex
Pilot Requirement Understanding and setup | [14 empty] | Radio | 30 | 10%
Understanding the manual flow of the process | Manual walk through of application | [9 empty] | 360 |  |  |  | Drop Down | 40 | 50%
Documentation | Basic documentation of process understanding and consideration for POC | [9 empty] | 600 |  |  |  | Checkbox | 35 | 22.5
Environment setup | Required hardware, software & code repo setup | [9 empty] | 420 |  |  |  | Button | 30 | 20
| Dev environment setup | [9 empty] | 420 |  |  |  | Text field | 30 | 30
Process Development | [14 empty] | Calendar | 60 | 40%
build basics | [14 empty] | Pop-up | 50
RPA Bot starts process on configurable schedule with a specific file target | Read the config file and Extract data like credentials, file paths, mailIDs etc from the file. | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 20% | 72 | considering file read by dictionary variable |  | if file path not accessible it will handle exception | Messages | 15
RPA Bot logs into Customer Gmail account a. Bot must successfully provide 2FA i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | 1. Navigate to the customer gmail account enter the ID and password. 2.Click on signin button.3.Provide 2FA 4.Verify the screen with expected result. |  |  |  | 2 | 3 |  | 1 | 1 | 10% | 236.5 | Assuming login portal contain 3 text fileds 1 button . For 2FA it could be verifying OTP . | text fields, button, popup , message | it will handle exception if url is not found ,credentials doesn’t match and if login button is not clickable
RPA Bot logs into Google CMS for Customer i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | 1. Navigate to the Google CMS for customer account enter the ID and password. 2.Click on signin button 3.Verify the screen with expected result. |  |  |  | 2 | 2 |  | 1 | 1 | 20% | 222 | Assuming the google CMS server for customer has credentials. | text fields, button, popup , message
Bot navigates to right hand side Content Manager Tab. Bot navigates to reports on left hand side | bot will select 'Content manager ' tab. Bot navigate to reports |  |  |  | 2 |  |  |  |  | 10% | 66
Bot selects Financial Report from tabs at top. Bot scrolls to Transaction Revenue Reports | bot will select finantial report from tab.Bot will scroll upto transaction revenue reports |  |  |  | 2 |  |  | 1 | 1 | 15% | 143.75 |  |  | it will hanle exception if tab option is disabled.
Bot updates filter view to Daily | Bot will update filter view to daily |  |  |  | 1 |  |  |  |  | 15% | 34.5 |  |  | 1. It will handle the exceptio if not able to do right click inside report 2.It will handle exception if file is not getting selection and not able to dowload.
Bot selects appropriate report 'Transactions Revenue Report' from the dropdown next to Rest of the World i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point, but continue to the next file | bot will select report 'Transaction revenue' |  | ` |  |  |  |  | 1 | 1 | 10% | 71.5 |  |  | it will hanle exception if tab option is disabled.
Bot collects the CSV file i. If Bot fails at this stage it posts to dashboard the Start and End time, client, filename, error point | Collecting the csv file from source server folder. |  |  |  |  | 1 |  | 1 | 1 | 10% | 104.5
Bot connects to VPN for Whip Customer AWS instance | considering check point VPN . Enter username and password. Then click on login. Wait few sec for auth otp. Enter generated OTP and click connect |  |  |  | 2 | 3 |  |  |  | 20% | 180 | considering like the check point VPN . Enter username and password. Then click on login. Wait few sec for auth otp. Enter generated OTP and click connect | button , text filed | 1.if username/password is invalid it will Hanlding exception 2.if AWS istance unable to open it will Handling the exception . 3. if Auth OTP is invalid/wrong it will Handling the exception
Bot logs into Customer CVM server using ftp client (currently - WinSCP) | Bot will log in into Customer CVM server using FTP client with credentials username and password |  |  |  | 1 | 2 |  |  |  | 20% | 108 | Assuming the Customer CVM server using FTP client has credentials username and password for Sign In purpose. | text fields, button | 1.invalid/expired/empty username or password 2.If expected portal wasn't received after logging in.
Bot drops the Transaction Rev Report CSV into destination folder | Move .csv file from source folder to the destination folder |  |  |  |  | 2 |  |  |  | 10% | 66 | Assuming there is one shared location for source and destination and bot has its access. |  | 1.source and destination folder not accessible to bot
Bot loads page for ingester | Redirect to the respective ingestor website |  |  |  |  | 1 |  |  |  | 10% | 33 |  |  | Handling the exception if respective URL is not get open.
Bot clicks the IngestNow button | click on button |  |  |  | 1 |  |  |  |  | 0 | 30 | Assuming it is a simple button | button | bot unable to find the IngestNow Button.
Bot checks original destination folder on Customer S3 folder to verify the file has been removed | Bot will check the status of file in source folder |  |  |  |  | 2 |  |  |  | 15% | 69 | Checking of the respective folder for absence of file will contain logical part. |  | Handling the exception for the file is present In source folder
File ingested into Customer CVM server or placed in error folder | Select the file . Pop up will appear to select the file location and upload.(Assumption) |  |  |  | 1 |  |  | 1 | 1 | 20% | 114 | Checking of the respective folder for presence of file will contain logical part. |  | Handling the exception for the file is absent in destination folder
Bot dashboard is updated with timestamp (start and end), client, filename, success also bot returns to CMS and repeats steps 4-18 for each applicable territory reported | Bot will generate the logs for the respective fields(Assumption)for the respective iteration repeats the steps for each resective iteration. |  |  |  |  | 3 |  |  |  | 15% | 103.5 | Considering dashbord as for showing logs .
For exception handling | [10 empty] | 120
Unit testing, reviews, fixes | [9 empty] | 25% | 443.5625
Bug fix after testing | Bug fixes if required | [8 empty] | 20% | 354.85
Integration of Code | [10 empty] | 300
Total of process development | [10 empty] | 48 | In Hrs
Deployment | Orchestrator set up : A. IIS configuration : 1. Web server - HTTP features 2. Web server - security 3. Web server - Application development 4. Web server - Web sockets 5. Web server - Management tools - Roles and features enable B. SSL server configuration | [9 empty] | 14
Deployment | Bot deployment | [9 empty] | 7
Deployment | Studio configuration | [9 empty] | 7
Testing on Prod | Test on production | [9 empty] | 14
Total of deployment | [10 empty] | 42 | In Hrs
Buffer (% of total efforts) | 10% | [9 empty] | 9 | in hrs
| Total - Implementation time | 5940 | 99
| Working hrs. per day | 7
| Team Size | 1
| Requirement understanding & Set up | 1800 | 30
| Number of days | 19
Considerations: | Access to Staging or Sandbox environment
Sample Input file is ready before development
Actual details of the data entry will be shared before the actual work. Based on the same, timelines may vary
Considering credentials and access of portal are handy with the developers.