## Estimated Efforts
| Activities | Steps / Actions | Estimated Time (Hours) | Details about the fields | Avg Execution time in seconds (based on eariler experince) | Manual /Automated/Common | Complexity parameters
| Requirement Understanding and setup | [5 empty] | Number of UI Element
| Understanding the manual flow of the process | Manual walk through of application | 7 |  |  |  | Selector options available |  | 1 | 13 | Dev 1
| Documentation | Documents for process understanding and development - PDD and SDD | 7 |  |  |  | Web responsiveness |  | 14 | 18 | Dev 2
| Environment setup | Required hardware, software & code repo setup | 7 |  |  |  | Data preprocessing involved |  | 19 | 25 | Dev 3
|  | Installation of all required application | 7 |  |  |  | Number of field validation
| Total Efforts for requirement and setup |  | 28 |  |  |  | Number of Pop-Ups
| Process Development | [5 empty] | Start Date |  | 2023-05-16 | 2023-05-22 | 2023-06-01 | 2023-06-08
1 | Login to Sales force | Login to Sales force app | 3 |  |  | Common
2 | Get customer info from excel and search for same | Read input excel and get customer whose contract needs to be updated | 8 |  |  | Common |  | Resources | Initial setup | Development | Deployment | Monitoring
3 | Navigate to subscription page for customer, in separate tab | Get Product code, Pricing Type Monthly recurring revenue, New Unit price per period from page | 4 |  |  | Manual | Architect |  | 1 | 0.25 | 0.25 | 0
4 | Navigate to Account details of corresponding subscription of customer | Amend contract information, Note Rebooking and De-Booking date would remain same as we see 'Contract start date' in contract page | 2 |  |  | Manual | RPA Engineer |  | 3 | 3 | 1 | 1
5 | On Contract page | Open contact details and perform following operations - select Sales campaign as 'Sales - Inboud' drop down in 'Response information' region and reload page, validate- Response field as ' Has campaign' | 3 |  |  | Manual | Man Days |  | 4 | 49 | 5 | 52 | depend on time for 4000 records processing + 15%
6 |  | Go to Opportunity and Select 'New Opportunity' | 2 |  |  | Manual | Working days |  | 4 | 17 | 5 | 52
7 | On New Opportunity page- Rebook | Record type of opportunity - select 'Standard Opportunity' | 1 |  |  | Manual
8 |  | Update 'Opportunity name' to as same Account name and few additional info | 5 |  |  | Manual
9 |  | Update Opportunity page with following fields - - Type - Primary Product interest - Close Date-start date from contract tab - Stage - Is Contract Modification - check - Contract Conversion- No - Skip Auto Provisioning- check - Opportunity currency to USD based on contract page - Save -> Navigates to Opportunity page | 9 |  |  | Common |  | Rate | Initial setup | Development | Deployment | Monitoring | Total
10 | On Opportunity page | Hover on Quote and click New Quote | 1 |  |  | Manual | Duration (days) |  | 4 | 17 | 5 | 52
11 |  | Navigates to Select quote type and select 'Draft Quote' and continue, it takes to Quote page | 2 |  |  | Manual | Architect | 1200 | 1 | 0.25 | 0.25 | 0
12 | On Quote Page - Rebooking | Select Start date is as of contract start date | 2 |  |  | Manual | RPA Engineer | 1000 | 3 | 3 | 1 | 1
|  | Amend end date which displayed in contract end date + 12 months and check override end date checkbox | 3 |  |  | Manual |  |  | 800 | 2671.4286 | 309.5238 | 2476.1905 | 6257.1429
13 |  | Update Invoice owner, select client name here | 4 |  |  | Manual |  | Mins (Manually) |  |  | Mins (RPA) | Total hrs (RPA)
14 |  | New Look up window for searching exact owner, validate Net suite customer from Account Customer ID field on Account page | 5 |  |  | Manual | Total transactions |  |  | 4000
15 |  | Update following fields - Primary Contact - Ship to contact - Bill to contact Get these values from Contract tab, bill to and Ship to fields | 7 |  |  | Manual | Time per transaction (with inbuilt automation) | 45 | mins | 2857 | 11 | 524 |  | 5
|  | in CPQ section, Sales rep. Info to filled with Account owner field from Account page/tab and Save | 5 |  |  | Manual | Time per transaction (manually) | 70 | mins | 1143 | 21 | 401 |  | 2
| On Edit Quote page - Rebooking | Add Product', navigates to search page and search product | 7 |  |  | Manual | % of transactions with inbuilt automation | 71.43% | [5 empty] | 420 | 365
16 |  | Check for contract - renewable and monthy | 2 |  |  | Manual | Transactions per person per day | 7
17 |  | In next page, add Quantity and Target Unit price and click Calculate and again on Save | 3 |  |  | Manual | Manual resources team size | 12
18 |  | Click on Opportunity link from Quote page itself from Quote details section | 1 |  |  | Manual | Duration of processing manually | 47.619 | days |  |  | 52
|  | Check Primary field from Quote details section and Save | 1 |  |  | Manual
19 | On Amend page-Edit quote | Navigate to URL | 2 |  |  | Common | Duration of processing manually | 2.381 | months |  |  | 1.74 | 2
20 |  | Change start date to Contract start date, some time custom segment appears, need to amend start date there as well End date also needs to same as End contract date | 5 |  |  | Manual | [5 empty] | 74%
21 |  | Change Quantity to 0 (Zero) | 1 |  |  | Manual
|  | Validate Annual recurring revenue with subtotal and Save. This will take open a debooking quote in same page | 2 |  |  | Manual |  |  |  |  | 45 | 11
22 | In De-booking Quote page | Click on Opportunity link from Quote page itself from Quote details section for the debooking and open it in new tab | 1 |  |  | Manual | Considerations: |  |  |  | 75 | 11*75/45
23 |  | Change the Sales Rep field with the accountOwner Name | 2 |  |  | Manual | - Need of rerun for any failed scenarios |  |  | Manual | RPA
24 |  | Validate Annual and monthly recurring revenue value to be negative in De-booking quote and also start date and end date fileds with the contract start date and End date | 3 |  |  | Manual |  |  | OneTime cost | 0 | 6257.1429
25 | In De-booking Oppurtunity Page | Update Opportunity page with following fields - - Type-Renewal - Primary Product interest - Close Date -Exclude from TAR Metrics - check -Is Contract Modification - check -Contract Conversion- No -Skip Auto Provisioning- check - Name and click on save | 9 |  |  | Common | Add manual steps for the additional work done manually (+55 mins) |  | Resources (#) | 12 | 1
26 |  | In Win Loss Detail Section under De-Booking win/Loss Reason select Corrective Transaction from drop down and click save | 1 |  |  | Manual | Based on number of UiPath licenses - efforts/timelines may vary |  | Resource ($) | 557 | 1000
27 | Duplicate Account Tab and click on Consolidated Transaction record | Hover on Consolidated Tranasaction Record and then click on New Consolidated Record | 1 |  |  | Manual | Salesforce and any other applications of our interest are up 24x7 |  | Duration | 2.381 | 1.74
28 | Record Type of new record | In the next page select Master Transaction under 'Record Type of new record' and click continue. | 2 |  |  | Manual | Downtime may vary and hence RoI as well |  | Cost | 15914.2857 | 7997.1429
29 |  | In next page update the following fields -Is Master Transaction- check -Quote - In_RebookingQuote -Opportunity Owner- and then click save | 5 |  |  | Manual | Post completion, extension of bot & maintenance will attract additional cost |  | Saving | 49.75%
30 | Create a duplicate tab for Master Consolidated page for De-booking | Under Consolidated Transaction Record, click on New consolidated transaction record | 2 |  |  | Manual |  |  | Dev Duration | 0 | 2
31 |  | In next page select General Transaction under Record Type of new type and click continue | 1 |  |  | Manual |  |  | RoI in time saved | -1.359 | months
32 |  | In next page update the following fields -Account -in_ProductName -Quotes - in_DebookingQuoteNumber -Type - Debooking -Contract - in_ContractNumber | 5 |  |  | Manual
33 |  | In Oppurtunity fields click on search button and type in_debookingOpportunityNumber and click on it and save and close this tab | 3 |  |  | Manual
34 | Create a duplicate tab for Master Consolidated page for Rebooking | Under Consolidated Transaction Record, click on New consolidated transaction record | 1 |  |  | Manual
35 |  | In next page select General Transaction under Record Type of new type and click continue | 1 |  |  | Manual
36 |  | In next page update the following fields -Account -in_ProductName -Quotes - in_RebookingQuoteNumber -Rebooking- check -Type - Rebooking -Contract - in_ContractNumber | 5 |  |  | Manual
|  | In Oppurtunity fields click on search button and type in_RebookingOpportunityNumber and click on it and save and close this tab | 4 |  |  | Manual
| Copy Master Consolidated transaction DR request number |  | 1
| Go on debooking Quote URL | in this page under 'Master Debook/rebook request' fill the in_DRNumber | 1 |  |  | Manual | Break up of automation vs manual transaction
| Go on rebooking Quote URL | in this page under 'Master Debook/rebook request' fill the in_DRNumber | 1 |  |  | Manual | Within manual transactions - refresh vs entire flow
| Reload Master Consolidated transaction tab | Under consolidated transaction record for the debook transaction copy the ARR value without the negative sign | 3 |  |  | Manual
| Go on rebooking Opportunity URL | Under 'Renewal Baseline' field add in_DebookARRValue and Save | 3 |  |  | Manual | automation order: with tool > manual refresh > complete manually
| In Master Consolidated transaction tab | Update the field 'Notes for approver' and 'internal Instruction' with the bebook and rebook quote links and also Net ARR Impact and Net TCV impact values | 1 |  |  | Common
| Navigate Debooking Quotes URL | Update the field 'Notes for approver' and 'internal Instruction' with the bebook and rebook quote links and also Net ARR Impact and Net TCV impact values | 1
| Navigate Rebooking Quotes URL | Update the field 'Notes for approver' and 'internal Instruction' with the bebook and rebook quote links and also Net ARR Impact and Net TCV impact values | 1
| Navigate Rebooking Opportunity URL | Update the field 'Description' and 'Win/Loss Notes' with the bebook and rebook quote links and also Net ARR Impact and Net TCV impact values | 1
| Navigate debooking Opportunity URL | Update the field 'Description' and 'Win/Loss Notes' with the bebook and rebook quote links and also Net ARR Impact and Net TCV impact values | 1
| RE-Framework/Input Folder/File setup | Setting up intput file and folder structure | 8
| Initiate Contract modification | Update the date /bill to contact and select the contract. | 5 | Date validation and calulations, Pop up handling. | 8
|  | Update Primary contact field | 3 | Data validation for email and name. | 6
|  | Update Ship to contact field | 3 | Data validation for email and name. | 6
|  | Tick on other and update the end date and generate the transaction. | 3 | Search and select the check box, Validate the date and add the date. | 8
|  | Verify product details, if not available add product details. | 5 | Read product name and verifying it. If not available add the details. | 10
|  | Wait till it completes creating the opportunity and quote | 6 | Wait till data is generated. If error occurres, refresh page, to see whether quote is generated or not. Notify on quote failure. Three retry for refresh. | 320
|  | Verify - Its created Debooking/opportunity/Quote | 10 | Copy the information of Quote and Opprtunity. Go to Debooking and edit Quote, select override check box and verify data on page as per requirement and cop the required information for further processing. | 15
| Open opportunity and quote and verify | Quote - copy info for further processing | 8 | Copy the reqiuired information and verify the data on page. Also copy the required information for further processing. | 15
|  | Click on re-direct on rebook/debook request | 8 | Copy the reqiuired information and verify the data on page. Also copy the required information for further processing. | 15
|  | Debook opportunity | 9 | Copy the reqiuired information and verify the data on page. Also copy the required information for further processing. | 15
|  | Correct end date | 3 | Select the check box and seelct the date and save the information. | 4
|  | Generate PDF | 8 | Click the button to generate PDF. Handle the Pop up, read the PDF and extract information to verify the data on PDF if its as per requirement | 10
|  | Open Consolidation details | 4 | Handle the pop up and update the notes on internal instruction section of the page. | 5
|  | Open Opportunity quote | 3 | Enter notes from consolidation details in additional instruction field | 2
|  | In Win-Loss section | 3 | Enter notes from consolidation details in additional instruction field | 2
|  | Update license | 4 | Get the data from Input file and update the license field. | 2
|  | Go to quote | 3 | Enter notes from consolidation details in additional instruction field | 2
| Go to Opportunity |  | 3 | Enter notes from consolidation details in additional instruction field | 2
|  | Notes Repeat for Re-booking and De-booking | 4 | Enter notes from consolidation details in additional instruction field | 2
|  | Go to re-booking quote | 5 | Update baseline amount and update. Also update contact conversion to 'No' | 2
| Exception Handling | System and Business exception handling and its solutions | 14 | Put exeception handling for all the tabs and Useful UI elements. Build logic to proceed for next transaction if a execption occurs.
| Code Review/ integrations | Review the code and fix the changes (32 hrs) | 7
| Testing | Testing code with few samples | 14
|  | Bug fixes if requried | 14
| Total of process development |  | 307 |  | 451
| Deployment | Deploy on production | 7
|  | Test on production & UAT | 28
| Total of deployment |  | 35
| Buffer (% of total efforts) | 10% | 34.2 | 35% | 158
|  | Total - Implementation | 376.2 |  | 11
|  | Working hrs per day | 7 | 18 | <- hrs (Bot run time per day)
|  | Team Size | 3 | 6 | Downtime (bot & maint)
|  | Number of days | 54
|  | Calendar days in a month | 21
|  | Number of prod licenses | 1
[5 empty] | Code running | Code running
[5 empty] | Bot running | Bot running
[5 empty] | browser | browser
[5 empty] | 4000 | 4000
|  |  | 14+8 | with automation tool | 70% | 2800
|  |  | 14+8+16 | manually with refresh | 18% | 720
|  |  | 14+44 | manually entire flow | 12% | 480
|  |  | 5 | integration & creating individual sets
14+8+16+44+5

## RoI - UiPath
Number of days in a month | 20 |  | Resources | Rate | Design |  | Development |  | Total Cost | [8 empty] | With tool | Manual
Resource Rate (Manual work) | 1000 |  |  |  | Allocation | Months | Allocation | Months | 1012.5 | [7 empty] | 4000 | 2840 | 1160 | transactions
Before Automation: |  |  | RPA Architect | 100 | 1 | 0.5 | 0.25 | 4 | 150 | [8 empty] | 11 | 21 | time per transaction
Team size | 12 |  | RPA Developer | 100 | 1 | 0.5 | 1 | 6 | 650 |  | 2 more months for support/maintenance/enhancements |  |  |  |  | 51.4815 | 55600 | 31240 | 24360 | total time for all transaction
Avg time per transaction - manual (mins) | 70 |  | RPA Developer | 100 | 0 | 0 | 0.25 | 4 | 100 |  | 4 more months part time for support/maintenance | [5 empty] | 1 | 0.56187 | 0.43813 | % time of total time for resp transaction
Transaction processed per day - manual | 2 |  | Project Manager | 100 | 0.25 | 0.5 | 0.25 | 4 | 112.5 |  | post support period, rates on hourly basis or extension as needed | [5 empty] | 1080 | 606.8201 | 473.1799 | time spent in a day for resp transactions
Avg time per transaction - with tool (mins) | 45 | [15 empty] | 77.6978 | 55.1655 | 22.5324
Transaction processed per day - with tool | 5 |  |  | Annual licensing |  |  | Monthly licensing |  |  | Monthly uploading |  |  | Annual licensing |  | Monthly uploading |  |  | 2840 | 1160
After Automation: |  |  |  | Breakeven: | 2170 months |  | Breakeven: | 10 months |  | 1000+ additional properties being uploaded by break even. |  | Month | Cost - Before | Cost - After | Properties Before | Properties After
Team size | 1 |  |  | 124474.2857 | 135251.6837 |  | 120000 | 26712.5 |  |  |  | 1 | 12000 | 20852.5 | 40 | 1073.4021
Avg time per transaction - manual (mins) | 21 |  | Development | 0 | 1012.5 | 1 | 0 | 1012.5 | 1 |  |  | 2 | 24000 | 21852.5 | 80 | 2146.8041
Avg time per transaction - with tool (mins) | 11 |  | License cost | 0 | 18840 | 1 | 0 | 0 | 1 |  |  | 3 | 36000 | 22852.5 | 120 | 3220.2062
Avg bot run time daily | 18 |  |  | Before | After |  | Before | After |  | Before | After | 4 | 48000 | 23852.5 | 160 | 4293.6082
Number of bots (prod licenses) running | 1 |  | Month 1 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 40 | 1113.4021 | 5 | 60000 | 24852.5 | 200 | 5367.0103
Transaction processed per day - manual | 22.268 |  | Month 2 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 80 | 2226.8041 | 6 | 72000 | 25852.5 | 240 | 6440.4124
Transaction processed per day - with tool | 55.6701 |  | Month 3 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 120 | 3340.2062 | 7 | 84000 | 26852.5 | 280 | 7513.8144
Implementation: |  |  | Month 4 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 160 | 4453.6082 | 8 | 96000 | 27852.5 | 320 | 8587.2165
% automation considered | 100% |  | Month 5 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 200 | 5567.0103 | 9 | 108000 | 28852.5 | 360 | 9660.6186
Development cost (one time) | 1012.5 |  | Month 6 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 240 | 6680.4124 | 10 | 120000 | 29852.5 | 400 | 10734.0206
UiPath Unattended bot license (monthly) | 1570 |  | Month 7 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 280 | 7793.8144 | 11 | 132000 | 30852.5 | 440 | 11807.4227
UiPath Unattended bot license (annual) | 18840 |  | Month 8 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 320 | 8907.2165 | 12 | 144000 | 31852.5 | 480 | 12880.8247 |  | 11 | 21
Server (MS Windows Server 2019 with std config): 01 |  |  | Month 9 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 360 | 10020.6186 | [6 empty] | 11
Database - use existing |  |  | Month 10 | 12000 | 1000 | 1 | 12000 | 2570 | 1 | 400 | 11134.0206 | [6 empty] | 11 | 21
Bot run time (mins) for 1 property (Avg setup) | 15 |  | Month 11 | 12000 | 1000 | 0 | 12000 | 2570 | 0 | 440 | 12247.4227 | [6 empty] | 11
Total properties a bot can automate in 24 hrs | 96 |  | Month 12 | 12000 | 1000 | 0 | 12000 | 2570 | 0 | 480 | 13360.8247 | [6 empty] | 11 | 21
Max manual resources we can have per bot | 6.8571 | [16 empty] | 11
Considerations | [17 empty] | 11 | 21
UiPath cost may vary | [17 empty] | 11
% automation coverage may vary |  |  |  | 45 | 70 | [12 empty] | 11 | 21
Development efforts/cost may vary |  |  |  | 21 | 11 | [12 empty] | 11
Implemented bot can automate more properties a day |  | tool | 21 | 2 | 42 |  | 22.268 | 467.6289 |  | 51.4286
This can be hosted over cloud and cost to be calculated |  | manual | 11 | 5 | 55 |  | 55.6701 | 612.3711 |  | 98.1818
existing manager to look after this later |  |  |  |  | 97 | 1080 | 11.134
Developer for maintenance full time > part time > hourly |  |  | 21 | 2 | 28.57% | 308.5714 | 14.6939
|  |  | 11 | 5 | 71.43% | 771.4286 | 70.1299
Other benefits |  |  |  | 7
Better accuracy in properties uploading
RoI will be faster for a bigger team size
Resources can be repurposed based on skills | [8 empty] | Dev efforts
post break even monthly 60% + savings | [8 empty] | Licens cost
automation can improve up to 75-80%
Below are Prerequisites for Installation of orchestrator. Install these on Orchestrator instance.
1. PowerShell - minimum required version: 4.0.
2. .NET Framework - minimum required version: 4.7.2.
3. IIS - minimum required version: 8. This is part of the Web Server (IIS) role. Following roles needs to be installed.
1. Expand Web Server (IIS) > Web Server > Common HTTP Features. The list contains the following items:
1. Default Document
2. HTTP Errors
3. Static Content
2. Expand Web Server (IIS) > Web Server > Security. The list contains the following items:
1. Request Filtering
2. URL Authorization
3. Windows Authentication
3. Expand Web Server (IIS) > Web Server > Application Development. The list contains the following items:
1. ASP.NET45
2. .NET Extensibility 4.5
3. Application Initialization
4. ISAPI Extensions
5. ISAPI Filter
6. WebSocket’s
4. Expand Web Server (IIS) > Web Server > Management Tools. The list displays the following items: IIS Management Console
5. Access Add Roles and Features Wizard > Features to enable the following item: Client for NFS.
4. ASP.Net Core IIS Module: Version should be part of the Hosting Bundle. Can be found here https://dotnet.microsoft.com/download/dotnet/thank-you/runtime-aspnetcore-3.1.5-windows-hosting-bundle-installer
5. URL Rewrite Module: Can be found here https://www.iis.net/downloads/microsoft/url-rewrite
6. SSL Certificate
1. Open IIS manager – Server certificate
2. Click on Self-signed certificate.
3. Specify name of the certificate, keep certificate store as Personal.
4. Click ok. (Keep the name of certificate for further use.)